## Sponsor Summary
2025 Affordable Housing Program
Owner-Occupied Sponsor Capacity Review
Sponsor Name:
AHP Project Number | Location | Project Type | Total Units | Units Complete by 4/30/2025 | Counseling In Process | Purchase Contract Signed | Home Inspection In Process | Rehabilitation Started | Additional Units Completed by 10/30/2025 | Units Remaining | Total Projected Units Completed by 10/30/2025 | Total Projected Units Remaining >10/30/2025 | Comments
| Urban | Purchase
| Rural | Rehabilitation
| Both | New Construction

## Analysis - HIDE (hidden)
2025 Affordable Housing Program
Owner-Occupied Sponsor Capacity Review
Sponsor Name:
AHP Project Number | Location | Project Type | Total Units | Units Complete by 4/30/2025 | Counseling In Process | Purchase Contract Signed | Home Inspection In Process | Rehabilitation Started | Additional Units Completed by 10/30/2025 | Units Remaining as of 4/30/2025 | Total Units Completed by 10/30/2025 | Units Remaining >10/30/2025 | Comments | Average Units/Month | 36 Month Limit | Units Funded as of 4/30/2025 | 1st DR Date | Last DR Date | Months | Average Units/Month Funded
| Rural | Purchase
| Urban | Rehabilitation
2020A07050 | Urban | Rehabilitation | 24 | 18 |  |  |  |  | 6 | 6 | 24 | 0 |  |  |  | 18 | 2022-08-01 | 2023-03-30 | 23 | 0.78261
|  |  | 24 | 10 |  |  |  |  | 6 | 14 | 16 | 8 |  |  |  | 10 | 2022-08-01 | 2023-01-30 | 23 | 0.43478
|  |  | 24 | 6 |  |  |  |  | 6 | 18 | 12 | 12 |  |  |  | 6 | 2022-08-01 | 2023-03-30 | 16 | 0.375
|  |  | 24 | 8 |  |  |  |  | 4 | 16 | 12 | 12 |  |  |  | 8 | 2022-08-01 | 2023-01-30 | 15 | 0.53333
|  |  | 24 | 3 |  |  |  |  | 4 | 21 | 7 | 17 |  |  |  | 3 | 2021-08-01 | 2022-08-01 | 7 | 0.42857
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
|  | Totals | 120 | 45 | 0 | 0 | 0 | 0 | 26 | 75 | 71 | 49 |  | #DIV/0! |  | 45 |  | Average | 16.8 | 0.51086
[15 empty] | Calculate based on award month/year |  |  |  | Calculate months between dates
Depending on selection; hide/blackout/reveal columns F,G (purchase) or H,I (rehab)
Possible to create the schedules below based on type selected in Column C?
| Can we then create another sheet, based on the sponsor data, like a carbon copy of Sheet 1. This is where the analysis is done | [11 empty] | Capacity Review Acquisition | Units |  | Capacity Review Rehabilitation | Units
| Hide the analysis sheet | [11 empty] | New AHP Units Requested | 72 |  | New AHP Units Requested | 72
[13 empty] | Add Units Remaining | 75 |  | Add Units Remaining >10/30/2024 | 49
[13 empty] | Minus Additional Units Completed | 26
[13 empty] | Total Units to Deliver | 121 |  | Total Units to Deliver | 121
[13 empty] | Months to Complete New & Prior Awards | 36 |  | Period in Months (DATES) | 36
[12 empty] | Based on DR activity + expected activity up to 10/2024 | Aver Unit/Month | 2.88 |  | Aver Unit/Month Needed
[13 empty] | Multiply by Aver Unit/Month | 103.68 |  | Multiply by Aver Unit/Month
[13 empty] | Minus Total Units to Deliver | 121 |  | Minus Total Units to Deliver
[13 empty] | Additional Capacity | -17.32 |  | Additional Capacity